## Dark
PROJECT: PDF Query Tool
Team Ciise |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Cabdulqaadir Ciise
Project start date: | 2023-09-10 |  |  |  |  | September | [20 empty] | October | [27 empty] | November
Scrolling increment: | 5 | time axis 2023-09-15 to 2023-11-09
Milestone description | Category | Assigned to | Progress | Start | Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Exploring Existing Solutions
Explore off the Shelf Solutions | On Track | Cabdul | 100% | 2023-09-15 | 5
What is LangChain? | On Track | Cabdul | 100% | 2023-09-18 | 10
What is Streamlit? | On Track | Cabdul | 100% | 2023-09-20 | 1
Create UML Artifacts | On Track
System Request | On Track | Cabdul | 100% | 2023-09-15 | 6
System Proposal | On Track | Cabdul | 100% | 2023-09-15 | 15
Functional Diagrams | On Track | Cabdul | 100% | 2023-09-23 | 6
Structural Diagrams | On Track | Cabdul | 100% | 2023-10-01 | 5
System Request Specification | On Track | Cabdul | 100% | 2023-10-10 | 5
Traceability Links | Low Risk | Cabdul | 100% | 2023-11-05 | 5
Change Management Plan | Low Risk | Cabdul | 100% | 2023-11-10 | 5
Codebase
Setup Repository | On Track | Cabdul | 100% | 2023-09-13 | 1
Create Project Site | On Track | Cabdul | 100% | 2023-10-05 | 2
Setup Environment | On Track | Cabdul | 100% | 2023-10-07 | 3
Implement PDF Processing | On Track | Cabdul | 100% | 2023-10-06 | 7
Build UI for PDF Upload | On Track | Cabdul | 100% | 2023-10-13 | 1
Adding Persistance | Med Risk | Cabdul | 100% | 2023-10-20 | 7
Add User Login | Med Risk | Cabdul | 100% | 2023-10-27 | 7
Explore Free LLM/Embedding Models | Med Risk | Cabdul | 50% | 2023-11-03 | 7
Deploy Application | Med Risk |  | 0% | 2023-11-10 | 7